## ProjectSchedule
RITU WEB APP
CSE-311L PROJECT
Members: Farhan Ishrak Tahmid - 2031458642, Md Zaed Iqbal Khan - 2031033642, Absara Chowdhury - 2031436642
|  |  | Project Start: | 2022-07-01
|  |  | Today: | 2022-06-29
|  |  | Display Week: | 1 |  |  | 2022-06-27 | [6 empty] | 2022-07-04 | [6 empty] | 2022-07-11 | [6 empty] | 2022-07-18 | [6 empty] | 2022-07-25 | [6 empty] | 2022-08-01 | [6 empty] | 2022-08-08 | [6 empty] | 2022-08-15 | [6 empty] | 2022-08-22
 | time axis 2022-06-27 to 2022-08-28
| TASK NAME AND DESCRIPTION | ASSIGNED TO | TASK PROGRESS | START DATE | END DATE | DAYS | time axis 2022-06-27 to 2022-08-28
BASIC DESIGN AND LEARNING
| LEARNING OF HTML CSS | All Group Members | 80% | 2022-07-01 | 2022-07-03 | 3
| BASIC FRONTEND SKELETON DESIGN | All Group Members | 90% | 2022-07-04 | 2022-07-09 | 6
| DJANGO-BASIC APPlICATION LAUNCHING AND LEARNING | All Group Members | 100% | 2022-07-10 | 2022-07-11 | 2
| CONNECTION BETWEEN WEBPAGES VIA DJANGO AS BACKEND | All Group Members | 45% | 2022-07-11 | 2022-07-14 | 4
DATABASE DESIGN AND SETUP
| BASIC TABLE STRUCTURE DESIGN | All Group Members | 0% | 2022-07-15 | 2022-07-16 | 2
| DESIGNING ALL ATTRIBUTES | All Group Members | 0% | 2022-07-17 | 2022-07-18 | 2
| CONNECTION WITH FRONTEND | ZAED,FARHAN | 0% | 2022-07-19 | 2022-07-20 | 2
| EXTRACTING DATA FROM FRONTEND | ZAED,FARHAN | 0% | 2022-07-21 | 2022-07-22 | 2
| IMPLEMENTING ALGORITHMS TO STORE DATA EFFICIENTLY | All Group Members | 0% | 2022-07-23 | 2022-07-25 | 3
| IMPLEMENTING ALGORITHMS TO SORT DATA | All Group Members | 0% | 2022-07-23 | 2022-07-25
| MEDIA HANDLING IN DATABASE | ABSARA,FARHAN | 0% | 2022-07-26 | 2022-07-27
IMPLEMENTING OTHER APPLICATIONS TO THE WEB APP
| DESIGN OF MARKETPLACE | ZAED,ABSARA | 0% | 2022-07-28 | 2022-07-29 | 2
| IMPLEMENTING DATA TABLES AND DATA STRUCTURES TO MANAGE MARKETPLACE | ZAED,ABSARA | 0% | 2022-07-29 | 2022-07-31 | 3
| INTEGRATING TIMER TO THE TASK WEB PAGES | ABSARA |  | 2022-08-01 | 2022-08-01
| DESIGNING ALGORITHMS FOR ADVERTISEMENT | ZAED,FARHAN | 0% | 2022-08-02 | 2022-08-03 | 2
| IMPLEMENTING ADS ON THE APP | ZAED | 0% | 2022-08-04 | 2022-08-06 | 3
| DESIGN OF ARTIFICIAL INTELLIGENCE, MACHINE LEARNING ALGORITHMS | ZAED,FARHAN | 0% | 2022-08-07 | 2022-08-09 | 3
| IMPLEMENTATION AND INTEGRATION OF AI & ML IN THE WEB APP | All Group Members | 0% | 2022-08-10 | 2022-08-13
| INTEGRATING MAPS IN THE TASK (PROPOSED) | FARHAN | 0% | 2022-08-12 | 2022-08-14
REDESIGN OF FRONTEND UI AND MAKING THE WEB APP RESPONSIVE
| INTEGRATING BOOTSTRAP AND JS | ABSARA,ZAED | 0% | 2022-08-14 | 2022-08-15 | 2
| REDESIGN OF FRONTEND UI | All Group Members | 0% | 2022-08-16 | 2022-08-17 | 2
TESTING AND BUG FIXING
| TESTING THE WEB APP WITH DIFFERENT SCENARIOS AND REAL WORLD USERS | All Group Members | 0% | 2022-08-18 | 2022-08-22 | 5
| FIXING THE BUGS FOUND IN THE TESTING PHASE | All Group Members | 0% | 2022-08-23 | 2022-08-27 | 5
Note on H8: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.